## ProjectSchedule
Usage of SDR to Decode Tire Pressure Monitoring System (TPMS)
EE 6900 – Software Defined Radio and Networking for the IoT
Kevin Hardin | Project Start: |  | 2023-01-09
Koffi Onipoh | Display Week: |  | 9 |  |  | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24
 | time axis 2023-03-06 to 2023-04-30
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-03-06 to 2023-04-30
1. Milestone 1
1.1 Group and Topic Declaration | Both | 100% | 2023-01-09 | 2023-02-06 | 29
2. Milestone 2
2.1 Project Proposal | Both | 100% | 2023-02-06 | 2023-03-13 | 36
3. Milestone 3
3.1 Setup MATLAB SDR environment | Both | 100% | 2023-03-13 | 2023-03-20 | 8
3.2 Record data from multiple vehicles | Both | 80% | 2023-03-21 | 2023-04-10 | 21
3.3 Begin data analysis | Both | 30% | 2023-04-11 | 2023-04-16 | 6
3.4 Progress report | Both | 100% | 2023-03-29 | 2023-04-03 | 6
4. Milestone 4
4.1 Create scripts to extract data content | Both | 50% | 2023-03-29 | 2023-04-05 | 8
4.2 Create scripts to build graphs | Both | 30% | 2023-04-06 | 2023-04-12 | 7
4.3 Begin Project Paper | Both | 100% | 2023-04-13 | 2023-04-17 | 5
4.4 Project Presentation | Both | 0% | 2023-04-13 | 2023-04-17 | 5
5. Milestone 5
5.1 Project Paper | Both | 15% | 2023-04-13 | 2023-05-01 | 19